## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Sourav | 2025-12-29 | Dataset contained missing and inconsistent email text values causing preprocessing errors. | Sprint 1 | Sourav | Data Issue | Cleaned dataset by removing null values and normalizing text. | 2025-12-30 | Closed | Data preprocessing improved
2 | Sourav | 2026-01-03 | TF-IDF vectorization produced incorrect feature dimensions during training. | Sprint 2 | Sourav | Feature Engineering | Adjusted TF-IDF parameters and refit vectorizer. | 2026-01-04 | Closed | Feature extraction fixed
3 | Sourav | 2026-01-10 | Spam detection model produced low accuracy during initial training. | Sprint 3 | Sourav | Model Performance | Tuned hyperparameters and selected a better ML algorithm. | 2026-01-12 | Closed | Accuracy improved
4 | Sourav | 2026-01-18 | Spam detection model produced low accuracy during initial training. | Sprint 4 | Sourav | Feature Logic | Updated keyword detection logic and added additional features. | 2026-01-19 | Closed | Urgency detection improved
5 | Sourav | 2026-01-28 | Error occurred while loading serialized models in the Streamlit application. | Sprint 5 | Sourav | Integration Issue | Fixed model loading path and corrected pickle file handling. | 2026-01-29 | Closed | Model integration successful
6 | Sourav | 2026-02-10 | Streamlit UI did not display prediction results correctly for some inputs. | Sprint 6 | Sourav | UI Bug | Updated UI logic and improved result display handling. | 2026-02-11 | Closed | Application functioning properly

## Sheet2
Logical
User Interface
Maintainability
Standards
Others